## week 2
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 2
Day | Date | Time IN | Time OUT | Total hours | Task
Wednesday | 11.03.2020 | 15:00 | 18:00 | 3 | Read the research paper shared by supervisor, going through the interface H5P
Thursday | 12.03.2020 | 15:00 | 18:00 | 3 | Going through the java script GitHub code shared by supervisor
Saturday | 14.03.2020 | 12:00 | 20:00 | 8 | Collecting the research paper, and starting to read through it
14

## week 3
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 3
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 16.03.2020 | 15:00 | 21:00 | 6 | After accumulating a lot of material through research papers, and videos, choosing the relevant content by marking them.
Tuesday | 17.03.2020 | 14:30 | 15:30 | 1 | Discuss the skeleton of pitch ppt
Tuesday | 17.03.2020 | 17:00 | 23:00 | 6 | Going through all the material given in pitch checklist, and watching the video of examples for good pitch, organizing the content for pitch
Wednesday | 18.03.2020 | 12:00 | 13:00 | 1 | Meeting with LEI team clients
Wednesday | 18.03.2020 | 16:00 | 21:00 | 5 | choosing themes, main points to focus, and adding content in the pitch ppt
Thursday | 19.03.2020 | 7:00 | 9:00 | 2 | Editing the pitch ppt and making sure to cover examples,and adding pictures before sending to the supervisor
Thursday | 19.03.2020 | 12:30 | 15:30 | 3 | Discuss the ppt of pitch presentation and Email the suppervisor the questions
Friday | 20.03.2020 | 13:30 | 16:30 | 3 | Discuss the modification of pitch ppt
Friday | 20.03.2020 | 18:00 | 22:00 | 4 | Editing the pitch ppt. editing the formatting, adding page number, editing grammar and removing some content which was irrelevant after getting some feedback from supervisor.
31

## week 4
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 4
Day | Date | Time IN | Time OUT | Total hours | Task
Wednesday | 25.03.2020 | 12:00 | 19:00 | 7 | Going through a lot of examples of parsons puzzle, to understand variations and feedback in solutions.
Thursday | 26.03.2020 | 20:00 | 23:00 | 3 | Trying some examples in H5P and understanding the interface
Friday | 27.03.2020 | 14:00 | 22:00 | 8 | Getting used to canvas and understanding the part of intergration of parsons puzzle into H5P
Friday | 27.03.2020 | 18:00 | 20:00 | 2 | Discuss the assignment of pitch presentation
Saturday | 28.03.2020 | 14:00 | 17:00 | 3 | Rehearse the pitch presentation
Sunday | 29.03.2020 | 14:00 | 18:00 | 4 | Record the pitch presentation
27

## week 5
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 5
Day | Date | Time IN | Time OUT | Total hours | Task
Wednesday | 01.04.2020 | 13:00 | 17:00 | 4 | Going through the checklist of business plan and researching some styles and format of business plan to develop
Friday | 03.04.2020 | 16:00 | 23:00 | 7 | Starting to develop the business plan, basically, adding the part 1 of project plan : which involves using pitch presentation as a reference for creating the Executive summary,project background and description,project goals and the extension of the project.
Friday | 03.04.2020 | 14:00 | 16:00 | 2 | Discuss milestone 1
Saturday | 04.04.2020 | 12:00 | 22:00 | 10 | Developing the part 2 of business plan,i.e., creating gantt chart which is implementation and schedule plan; specifying the roles and responsibilities and lastly, creating the communication plan.
Sunday | 05.04.2020 | 10:00 | 12:00 | 2 | Discuss business plan
Sunday | 05.04.2020 | 14:00 | 18:00 | 4 | Editing the project plan, checking the grammar, font and adding references
29

## week 6
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 6
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 04.04.2020 | 14:00 | 16:00 | 2 | Reflect the process of the project, summarize the issues, email the supervisor
Tuesday | 05.04.2020 | 15:00 | 15:30 | 0.5 | Client Meeting with the Supervisor
Tuesday | 05.04.2020 | 15:30 | 16:00 | 0.5 | summarize client meeting handin documents
Wednesday | 06.04.2020 | 11:00 | 20:00 | 9 | Creating the GUI for the instructor side by analysing the h5p interface and adding the necessary options to implement the parsons puzzle
Thursday | 07.04.2020 | 9:00 | 16:00 | 7 | Creating the summary report to subsantiate my learnings for the project
Friday | 08.04.2020 | 16:00 | 20:00 | 4 | Analyzing more ways to improve the GUI by researching different styles of GUI used by instructors
Saturday | 09.04.2020 | 10:00 | 16:00 | 6 | Researching about the integration of H5P into Drupal
29
,

## mid-semester break
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : mid-semester break
Day | Date | Time IN | Time OUT | Total hours | Task
Tuesday | 14.04.2020 | 12:00 | 16:00 | 4 | Understanding the integration of parsons puzzle into canvas using H5P with Drupal acting as self-host
Wednesday15.05.2020 | 16.04.2020 | 11:00 | 17:00 | 6 | Understanding the interface of H5P Drag and Drop, Fill in the blanks function by using the interface and checking out every options usage
Tuesday | 21.04.2020 | 12:00 | 16:00 | 5 | Taking the feedback from supervisor and working over to get better view of distractors, and the affect of mapping different levels: beginner, fundamentals and mastery
Saturday | 24.04.2020 | 10:00 | 14:00 | 4 | Searching for feedback of instructors for parsons puzzle
19

## week 7
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 7
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 27.04.2020 | 15:30 | 16:30 | 1 | Group Meeting: Discuss Milestone 1
Tuesday | 28.04.2020 | 14:00 | 18:00 | 4 | Trying to understand the structure and functioning of js-parsons code in github to get the essence of basic functionaities to be implemented for milestone 1, so that it can help me for testing.
Wednesday | 29.04.2020 | 13:00 | 19:00 | 6 | Looking at different types of parsons puzzle and checking how to mix two types and what more functionaltites we can work upon in design and the difficulty level of implementing it for the final milestone
Thursday | 27.04.2020 | 9:00 | 13:00 | 4 | Understanding the purpose of milestone report. Reading the examples and getting the essence of how to write the milestone report
Friday | 01.05.2020 | 16:00 | 20:00 | 4 | Writing the milestone report of the group
Saturday | 02.05.2020 | 10:00 | 15:00 | 5 | Researching about the testing tools, the testing plan examples and reading the modules of testing the software
24

## week 8
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 8
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 04.05.2020 | 11:00 | 18:00 | 7 | Installation of the environment for testing: Node.js, Git for destop, H5P command line inteface, acquia dev desktop 2.
Wednesday | 06.05.2020 | 12:00 | 18:00 | 6 | Creating new website using Acquia, by installing drupal 7.69 and integrating the H5P library with drupal to test the H5P customised function.
Thursday | 07.05.2020 | 14:00 | 18:00 | 4 | After integrating H5P into Drupal, adding the code pf first milestone in GitHub: customised H5P function into Drupal for testing and start to create the test cases by getting used to the function.
Friday | 08.05.2020 | 16:00 | 19:00 | 3 | Researching about automatic test scripts and how to creat test scripts for testing. Reading about unit, integration and defect testing.
Saturday | 02.05.2020 | 10:00 | 15:00 | 5 | Doing unit testing and integration testing on parsons puzzle funcion. Moreover, while testing finding if finding some issues, reporting it to the developer.(for example: errors or buttons not working).
25

## week 9
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 9
Day | Date | Time IN | Time OUT | Total hours | Task | Column1
Monday | 11.05.2020 | 11:00 | 21:00 | 10 | Writing the testing report and completing till section 4. | .
Wednesday | 13.05.2020 | 13:00 | 21:00 | 8 | Writing the final milestone report after discussion with the team and completing the remaining testing report (risks, gantt chart , testing table, screenshots).
Thursday | 14.05.2020 | 15:00 | 18:00 | 3 | Brainstorming session with the team about design and how to conclude the research we have done all along.
Friday | 08.05.2020 | 14:00 | 19:00 | 5 | Editing the testing report and researching about the design of creation of parsons puzzle and evaluating different types and their significance.
26

## week 10
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 10
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 18.05.2020 | 13:00 | 19:00 | 6 | Drafting the final design document by structuring thoughts and creating the student and instructure interface GUI
Wednesday | 20.05.2020 | 14:00 | 15:00 | 1 | Meeting with the supervisor. Report the progress. Discuss the goal for the final milestone: feedback function and fill in the blanks.
Thursday | 21.05.2020 | 10:30 | 12:30 | 2 | Discussion of final design document, final milestone and reflecting on previous communication gap, to not commit it into final milestone
|  | 14:00 | 16:00 | 2 | Testing the feedback part of the the Drag and Drop function committed to GitHub
Friday | 22.05.2020 | 11:00 | 19:00 | 7 | Updating the final design document
Saturday | 23.05.2020 | 11:00 | 16:00 | 5 | Going through poster examples and collecting data for poster, getting idea about demo and final report
23

## week 11
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 11
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 24.05.2020 | 14:00 | 21:00 | 7 | Creating the GUI for the design document and specifying the content to be added for future extension of design
Thursday | 27.05.2020 | 13:00 | 18:00 | 5 | Structuring the poster layout, and starting to finalise the heading and add the content in parts of Introduction and Tools.
Friday | 28.05.2020 | 10:00 | 17:00 | 7 | Assessing the implementation of the design done by technical team and thinking how to extend the project design
Saturday | 29.05.2020 | 12:00 | 18:00 | 6 | Finalising the design document, and combining the GUI with content
25

## week 12
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 12
Day | Date | Time IN | Time OUT | Total hours | Task
Friday | 05.06.2020 | 11:00 | 21:00 | 10 | Adding the content into poster, and summarising the universal design key concepts
Saturday | 06.06.2020 | 15:00 | 20:00 | 5 | Understanding the predefined syntax rule of the H5P customised function and analysing the integration implemented in second version, testing the version.
Sunday | 07.06.2020 | 12:00 | 22:00 | 10 | Editing the meeting minutes from week 7 till week 12, and finalising the poster by doing grammatical checks and combining the parts together
25

## week 13
MCI Project Weekly Time Sheet
Team : 27 |  | Student ID | : a1760776 |  | Week : 13
Day | Date | Time IN | Time OUT | Total hours | Task
Monday | 08.06.2020 | 11:00 | 19:00 | 8 | Updating the poster and the final design document by taking feedback from the supervisor
Tuesday | 19.06.2020 | 15:00 | 16:00 | 1 | Meeting with the supervisor, showing the demo video and taking suggestion for structuring demo
9