## Week3
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2020-03-16 | 13:00 | 18:00 | 5 | Setting up the development environment - Canvas |  | Failed to make it work
Tuesday | 2020-03-17 | 9:30 | 13:30 | 4 | Setting up the development environment - Canvas |  | Failed to make it work
|  | 14:30 | 15:30 | 1 | Discuss the skeleton of pitch ppt | For Pitch Presentation | The skeleton of pitch ppt
|  | 15:15 | 19:45 | 4.5 | Setting up the development environment - Canvas |  | Failed to make it work and try to use another platform
Wednesday | 2020-03-18 | 12:00 | 13:00 | 1 | Meeting with LEI team clients | Requirements gathering for the pitch presentation | Specified requirements. / Connect the corrent person from the MyUni team to get more technical support.
Thursday | 2020-03-19 | 7:30 | 9:30 | 2 | Modified the ppt of pitch presentation | For Pitch Presentation
|  | 12:30 | 15:30 | 3 | Discuss the ppt of pitch presentation and Email the suppervisor the questions | For Pitch Presentation
Friday | 2020-03-20 | 13:30 | 16:30 | 3 | Discuss the modification of pitch ppt | For Pitch Presentation
Saturday | 2020-03-21 | 13:00 | 17:00 | 4 | Setting up the development environment - Drupal |  | Proceding
Sunday | 2020-03-22
|  |  | Total | 27.5

## Week4
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 4
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2020-03-23 | 9:00 | 14:00 | 5 | Setting up the development environment - Drupal |  | Succeed
Tuesday | 2020-03-24 | 15:00 | 18:00 | 3 | Learning H5P |  | Proceding
Wednesday | 2020-03-25 | 10:00 | 12:00 | 2 | Learning H5P |  | Proceding
Thursday | 2020-03-26 | 14:00 | 18:00 | 4 | Connect H5P and Drupal |  | Failed
Friday | 2020-03-27 | 18:00 | 20:00 | 2 | Discuss the assignment of pitch presentation | For Pitch Presentation
|  | 9:00 | 11:00 | 2 | Write the speech | For Pitch Presentation
Saturday | 2020-03-28 | 14:00 | 17:00 | 3 | Rehearse the pitch presentation | For Pitch Presentation
Sunday | 2020-03-29 | 14:00 | 18:00 | 4 | Record the pitch presentation | For Pitch Presentation | The presentation video
|  |  | Total | 25

## Week5
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2020-03-30
Tuesday | 2020-03-31 | 9:00 | 12:00 | 3 | Upload H5P Hello World tutorial |  | Failed
|  | 14:30 | 19:00 | 4.5 | Keep working on H5P tutorial |  | Failed
Wednesday | 2020-04-01 | 14:00 | 19:00 | 5 | H5P package |  | Failed
Thursday | 2020-04-02 | 14:00 | 18:00 | 4 | H5P package |  | Succeed
Friday | 2020-04-03 | 9:00 | 12:00 | 3 | H5P tutorial uploading |  | Succeed
|  | 14:00 | 16:00 | 2 | Discuss Milestone 1 | For Business Plan
Saturday | 2020-04-04 | 10:00 | 12:00 | 2 | H5P tutorial modification |  | Succeed
Sunday | 2020-04-05 | 9:00 | 10:00 | 1 | Review and edit the Business Plan | For Business Plan | Business Plan
|  | 10:00 | 12:00 | 2 | H5P uploading |  | Succeed
|  |  | Total | 26.5

## Week6
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2020-04-06 | 9:00 | 12:00 | 3 | Work on H5P integrating with Canvas
|  | 14:00 | 16:00 | 2 | Reflect the process of the project, summarize the issues, email the supervisor
Tuesday | 2020-04-07 | 15:00 | 3:30 | 0.5 | Client Meeting with the supervisor | Redirect the objectives of the project
|  | 15:30 | 16:00 | 0.5 | Group meeting |  | summarize cline meeting, handing documents
Wednesday | 2020-04-08 | 9:30 | 11:30 | 2 | Summary report |  | Design the structure and list dot points
|  | 11:30 | 12:00 | 0.5 | Timesheet documents
Thursday | 2020-04-09 | 9:00 | 12:30 | 3.5 | Summary report |  | Finished
Friday | 2020-04-10 | 9:00 | 12:00 | 3 | Learning JavaScript
|  | 14:00 | 18:00 | 4 | Learning JavaScript
Saturday | 2020-04-11 | 13:00 | 18:00 | 5 | Learning JavaScript
Sunday | 2020-04-12 | 18:00 | 22:00 | 4 | Learning JavaScript
|  |  | Total | 28

## MidBreak
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 7
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-04-13 | 9:00 | 12:00 | 3 | Learning JavaScript
|  | 14:00 | 17:00 | 3
Tuesday | 2020-04-14 | 9:00 | 9:30 | 0.5 | TimeSheet Document
|  | 14:00 | 18:00 | 4 | Learning JavaScript
Wednesday | 2020-04-15 | 9:00 | 12:00 | 3 | Learning JavaScript
|  | 14:00 | 18:00 | 4 | Learning JavaScript
Thursday | 2020-04-16
Friday | 2020-04-17 | 19:00 | 22:00 | 3 | Learning JavaScript
Saturday | 2020-04-18
Sunday | 2020-04-19 | 14:00 | 19:00 | 5 | Learning JavaScript
Monday | 2020-04-20 | 9:00 | 12:00 | 3 | Learning Drupal7
|  | 14:00 | 18:00 | 4 | Learning Drupal7
Tuesday | 2020-04-21 | 14:00 | 17:00 | 3 | Brain storm about the puzzle design
Wednesday | 2020-04-22
Thursday | 2020-04-23 | 19:00 | 22:00 | 3 | Learning how h5p works
Friday | 2020-04-24
Saturday | 2020-04-25 | 9:00 | 12:00 | 3 | Try to create a type of parson puzzle
|  | 14:00 | 18:00 | 4 | Try to create a type of parson puzzle
Sunday | 2020-04-26 | 14:00 | 18:00 | 4 | Try to create a type of parson puzzle
|  |  | Total | 49.5

## Week7
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 7
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-04-27 | 15:30 | 16:30 | 1 | Group Meeting: Discuss Milestone 1
Tuesday | 2020-04-28 | 9:00 | 12:00 | 3 | Working on the H5P library pack issue
|  | 14:00 | 18:00 | 4 | Working on the H5P library pack issue
Wednesday | 2020-04-29 | 9:00 | 12:00 | 3 | Working on how puzzles results show on Canvas
|  | 14:00 | 19:00 | 5 | Install View modules in Drupal to show the results
Thursday | 2020-04-30 | 10:00 | 14:00 | 2 | Figuring out how H5P drag and drop works
|  | 15:00 | 20:00 | 5 | Figuring out how H5P drag and drop works
Friday | 2020-05-01 | 10:00 | 17:00 | 7 | Look into parsons puzzle js on github
Saturday | 2020-05-02 | 11:00 | 16:00 | 5 | Look into parsons puzzle js on github
Sunday | 2020-05-03 | 10:00 | 20:00 | 10 | Build a list of parsons puzzle
|  |  | Total | 45

## week8
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 8
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-05-04 | 9:00 | 12:00 | 3 | Build a list of parsons puzzle
|  | 14:00 | 17:00 | 3 | Build a list of parsons puzzle
|  | 20:00 | 22:00 | 2 | Build a list of parsons puzzle
Tuesday | 2020-05-05 | 9:00 | 12:00 | 3 | Draw datagrams of js-parson
Wednesday | 2020-05-06 | 14:00 | 18:00 | 4 | Draw datagrams of js-parson
Thursday | 2020-05-07 | 14:00 | 18:00 | 4 | Connect js-parson with H5P
Friday | 2020-05-08 | 9:00 | 12:00 | 3 | Connect js-parson with H5P
Saturday | 2020-05-09 | 14:00 | 18:00 | 4 | Connect js-parson with H5P
Sunday | 2020-05-10
|  |  | Total | 26

## week9
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 9
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-05-11 | 9:00 | 12:00 | 3 | Paper research
Tuesday | 2020-05-12 | 9:00 | 12:00 | 3 | Literature Review of Parsons Puzzle
|  | 14:00 | 16:00 | 2 | Literature Review of Parsons Puzzle
|  | 16:00 | 18:00 | 2 | Design the system and create a document about design
Wednesday | 2020-05-13 | 14:00 | 18:00 | 4 | Design the system and create a document about design
Thursday | 2020-05-14
Friday | 2020-05-15 | 14:00 | 18:00 | 4 | Design the system and create a document about design
Saturday | 2020-05-16 | 9:00 | 12:00 | 3 | Work on the connection between H5P and Drupal
Sunday | 2020-05-17 | 19:00 | 22:00 | 3 | Work on the connection between H5P and Drupal
|  |  | Total | 24

## week10
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 10
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-05-18 | 9:00 | 18:00 | 9 | Work on the system design.
Tuesday | 2020-05-19
Wednesday | 2020-05-20 | 14:00 | 15:00 | 1 | Meeting with the supervisor. Report the progress. Set the goal of next stage and the final: feedback functions.
Thursday | 2020-05-21
Friday | 2020-05-22 | 10:00 | 18:00 | 8 | Work on the re-construction of the H5P parsons library
Saturday | 2020-05-23 | 9:00 | 15:00 | 6 | Work on the fill in the blank function
Sunday | 2020-05-24 | 15:00 | 18:00 | 3 | Work on the fill in the blank function
|  |  | Total | 27

## week11
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 11
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-05-25
Tuesday | 2020-05-26 | 9:00 | 21:00 | 12 | Debug fill in the blank function
Wednesday | 2020-05-27 | 9:00 | 19:00 | 10 | Debug fill in the blank function
Thursday | 2020-05-28 | 10:00 | 12:00 | 2 | debug fill in the blank function
|  | 13:30 | 14:00 | 0.5 | Group meeting: Communicate the progress of implementation.
|  | 14:00 | 17:00 | 3 | debug fill in the blank function
Friday | 2020-05-29
Saturday | 2020-05-30
Sunday | 2020-05-31
|  |  | Total | 27.5

## week12
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 12
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-06-01
Tuesday | 2020-06-02
Wednesday | 2020-06-03 | 10:00 | 18:00 | 8 | Fix code bugs for UI
Thursday | 2020-06-04 | 14:30 | 15:00 | 0.5 | Group meeting: Discuss the structure and content for poster and demo
Friday | 2020-06-05
Saturday | 2020-06-06 | 10:00 | 18:00 | 8 | Debug fill in the blank
Sunday | 2020-06-07 | 10:00 | 23:00 | 13 | Contruct system architecture and key components of the Poster
|  |  | Total | 29.5

## week13
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 13
Day | Date | Time In | Time Out | Total hours | Task
Monday | 2020-06-08 | 10:00 | 23:00 | 13 | Test and final debug of code
Tuesday | 2020-06-09 | 10:00 | 15:00 | 5 | Make demo video version 1
|  | 15:00 | 16:00 | 1 | Meeting with supervisor: report progress and prepare for the final
Wednesday | 2020-06-10 | 11:00 | 14:00 | 3 | Discuss the process and details of final presentation
|  | 15:00 | 21:00 | 6 | Record and make demo video version 2
Thursday | 2020-06-11 | 8:00 | 10:00 | 2 | Final Presentation Preparation: write speech and modify demo video
|  | 10:00 | 10:30 | 0.5 | Rehearse with Supervisor
|  | 10:30 | 14:00 | 3.5 | Practice demo
|  | 14:00 | 15:00 | 1 | Final Presentation
Friday | 2020-06-12
Saturday | 2020-06-13 | 9:30 | 21:00 | 11.5 | Write final report
Sunday | 2020-06-14 | 10:00 | 0:00 | 14 | Write final report
|  |  | Total | 60.5

## template
MCI Project Weekly Time Sheet
Team | 27 | Student ID | a1751414 |  |  | Week | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2020-04-13
Tuesday | 2020-04-14
Wednesday | 2020-04-15
Thursday | 2020-04-16
Friday | 2020-04-17
Saturday | 2020-04-18
Sunday | 2020-04-19
|  |  | Total | 0